## Table 1
Assignment No.:-01 (Div-A)
Create Project Plan for Mobile App Development
▪ Specify project name and start (or finish) date.
▪ Identify and define project tasks.
▪ Define duration for each project task.
▪ Define milestones in the plan
▪ Define dependency between tasks
▪ Define project calendar.
▪ Define project resources and specify resource type
▪ Assign resources against each task and baseline the project plan
Project Plan: Mobile App Development
Project Start Date: August 1, 2024
Project End Date: December 20, 2024
Project Tasks and Schedule
Task ID |  |  | Task Name | [18 empty] | Duration | [9 empty] | Start Date | [13 empty] | End Date | [10 empty] | Dependencies
1 |  |  | Project Initiation | [18 empty] | 5 days | [9 empty] | August 1, 2024 | [13 empty] | August 5, 2024 | [10 empty] | None
2 |  |  | Requirement Gathering and Analysis | [18 empty] | 10 days | [9 empty] | August 6, 2024 | [13 empty] | August 19, 2024 | [10 empty] | 1
3 |  |  | Design Phase | [18 empty] | 20 days | [9 empty] | August 20, 2024 | [13 empty] | September 16, 2024 | [10 empty] | 2
4 |  |  | Development Phase | [18 empty] | 45 days | [9 empty] | September 17, 2024 | [13 empty] | November 19, 2024 | [10 empty] | 3
5 |  |  | Testing Phase | [18 empty] | 20 days | [9 empty] | November 20, 2024 | [13 empty] | December 17, 2024 | [10 empty] | 4
6 |  |  | Deployment | [18 empty] | 3 days | [9 empty] | December 18, 2024 | [13 empty] | December 20, 2024 | [10 empty] | 5
Project Tasks and Schedule 01-Aug 21-Aug 10-Sep 30-Sep 20-Oct 09-Nov 29-Nov 19-Dec Project Initiation Requirement Gathering and Analysis Design Phase Development Phase Testing Phase Deployment
[5 empty] | Deployment | [11 empty] | Testing Phase | [9 empty] | Development Phase | [12 empty] | Design Phase | [11 empty] | Requirement Gathering and Analysis | [5 empty] | Project Initiation
Start Date |  |  |  |  | 18-Dec | [11 empty] | 20-Nov | [9 empty] | 17-Sep | [12 empty] | 20-Aug | [11 empty] | 06-Aug | [5 empty] | 01-Aug
Duration |  |  |  |  | 3 | [11 empty] | 20 | [9 empty] | 45 | [12 empty] | 20 | [11 empty] | 10 | [5 empty] | 5
Milestones
Milestone ID | [6 empty] | Milestone Description | [29 empty] | Date
M1 | [6 empty] | Project Kickoff | [29 empty] | August 1, 2024
M2 | [6 empty] | Requirements Document Completed | [29 empty] | August 19, 2024
M3 | [6 empty] | Design Approval | [29 empty] | September 16, 2024
M4 | [6 empty] | Development Complete | [29 empty] | November 19, 2024
M5 | [6 empty] | Testing Complete | [29 empty] | December 17, 2024
M6 | [6 empty] | App Deployment | [29 empty] | December 20, 2024
Project Calendar
 Working Days: Monday to Friday
 Holidays: Public holidays and weekends
Project Resources
Resource ID | [5 empty] | Resource Name | [20 empty] | Resource Type
PM | [5 empty] | Project Manager | [20 empty] | Management
BA | [5 empty] | Business Analyst | [20 empty] | Analysis
Designer | [5 empty] | UI/UX Designer | [20 empty] | Design
MD | [5 empty] | Mobile Developer | [20 empty] | Development
QA | [5 empty] | Quality Assurance Tester | [20 empty] | Testing
DE | [5 empty] | Deployment Engineer | [20 empty] | Deployment
Resource Allocation
Task ID |  |  |  | Task Name | [29 empty] | Resources Assigned
1 |  |  |  | Project Initiation | [29 empty] | PM: 100%
2 |  |  |  | Requirement Gathering and Analysis | [29 empty] | PM: 50%, BA: 100%
3 |  |  |  | Design Phase | [29 empty] | PM: 25%, Designer: 100%, BA: 50%
4 |  |  |  | Development Phase | [29 empty] | PM: 25%, Designer: 25%, MD: 100%
5 |  |  |  | Testing Phase | [29 empty] | PM: 25%, QA: 100%, MD: 50%
6 |  |  |  | Deployment | [29 empty] | PM: 50%, DE: 100%
Baseline Project Plan
 Baseline Date: August 1, 2024
 A baseline will be set on August 1, 2024, after the Project Initiation phase is complete. This baseline will be used to track project progress and performance against the initial plan.
Assignment No.:-01 (Div-B)
Create Project Plan for Website Design
▪ Specify project name and start (or finish) date.
▪ Identify and define project tasks.
▪ Define duration for each project task.
▪ Define milestones in the plan
▪ Define dependency between tasks
▪ Define project calendar.
▪ Define project resources and specify resource type
▪ Assign resources against each task and baseline the project plan
Project Name: Website Design Project | [27 empty] | Start Date: 2024-07-15 | [20 empty] | Finish Date: 2024-10-15
Project Tasks
Task ID |  | Task Name | [9 empty] | Duration (Days) | [7 empty] | Start Date | [5 empty] | Finish Date | [6 empty] | Dependencies | [12 empty] | Milestones | [7 empty] | Resources | [5 empty] | Resource Type
1 |  | Project Initiation | [9 empty] | 2 | [7 empty] | 2024- 07-15 | [5 empty] | 2024- 07-16 | [6 empty] | - | [12 empty] | Project Kickoff | [7 empty] | Project Manager | [5 empty] | Human
2 |  | Requirement Gathering | [9 empty] | 5 | [7 empty] | 2024- 07-17 | [5 empty] | 2024- 07-21 | [6 empty] | 1 | [12 empty] | Requirement Document | [7 empty] | Business Analyst | [5 empty] | Human
3 |  | Site Structure Planning | [9 empty] | 3 | [7 empty] | 2024- 07-22 | [5 empty] | 2024- 07-24 | [6 empty] | 2 | [12 empty] | Site Map Created | [7 empty] | UX Designer | [5 empty] | Human
4 |  | Design Phase | [9 empty] | 10 | [7 empty] | 2024- 07-25 | [5 empty] | 2024- 08-03 | [6 empty] | 3 | [12 empty] | Initial Design Completed | [7 empty] | UI Designer, Graphic Designer | [5 empty] | Human
5 |  | Design Review and Approval | [9 empty] | 4 | [7 empty] | 2024- 08-04 | [5 empty] | 2024- 08-07 | [6 empty] | 4 | [12 empty] | Design Approved | [7 empty] | Project Manager, Client | [5 empty] | Human
6 |  | Development Phase | [9 empty] | 20 | [7 empty] | 2024- 08-08 | [5 empty] | 2024- 08-27 | [6 empty] | 5 | [12 empty] | Frontend | [7 empty] | Web | [5 empty] | Human
[46 empty] | and Backend | [7 empty] | Developer, Backend
[46 empty] | Completed | [7 empty] | Developer
7 |  | Content Creation | [9 empty] | 10 | [7 empty] | 2024- 08-28 | [5 empty] | 2024- 09-06 | [6 empty] | 2 | [12 empty] | Content Ready | [7 empty] | Content Writer | [5 empty] | Human
8 |  | Integration and Testing | [9 empty] | 7 | [7 empty] | 2024- 09-07 | [5 empty] | 2024- 09-13 | [6 empty] | 6, 7 | [12 empty] | Testing Completed | [7 empty] | QA Tester | [5 empty] | Human
9 |  | User | [9 empty] | 5 | [7 empty] | 2024- 09-14 | [5 empty] | 2024- 09-18 | [6 empty] | 8 | [12 empty] | UAT Completed | [7 empty] | Client, QA Tester | [5 empty] | Human
Acceptance Testing
(UAT)
Task ID |  | Task Name | [9 empty] | Duration (Days) | [7 empty] | Start Date | [5 empty] | Finish Date | [6 empty] | Dependencies | [12 empty] | Milestones | [7 empty] | Resources | [5 empty] | Resource Type
10 |  | Final Revisions | [9 empty] | 4 | [7 empty] | 2024- 09-19 | [5 empty] | 2024- 09-22 | [6 empty] | 9 | [12 empty] | Revisions Completed | [7 empty] | Web Developer, UI Designer | [5 empty] | Human
11 |  | Deployment | [9 empty] | 3 | [7 empty] | 2024- 09-23 | [5 empty] | 2024- 09-25 | [6 empty] | 10 | [12 empty] | Site Live | [7 empty] | Web Developer | [5 empty] | Human
12 |  | Project Closure | [9 empty] | 2 | [7 empty] | 2024- 09-26 | [5 empty] | 2024- 09-27 | [6 empty] | 11 | [12 empty] | Project Completed | [7 empty] | Project Manager | [5 empty] | Human
Project Tasks 15-Jul 25-Jul 04-Aug 14-Aug 24-Aug 03-Sep 13-Sep 23-Sep 03-Oct 13-Oct Project Initiation Requirement Gathering Site Structure Planning Design Phase Design Review and Approval Development Phase Content Creation Integration and Testing User Acceptance Testing (UAT) Final Revisions Deployment Project Closure
[9 empty] | Project Closure |  |  |  |  | Deploy ment |  |  |  |  | Final Revisio ns |  |  |  | User Accept ance Testing (UAT) | [6 empty] | Integra tion and Testing |  |  |  |  | Conten t Creatio n | [5 empty] | Develo pment Phase | [5 empty] | Design Review and Approv al | [5 empty] | Design Phase |  | Site Structu re Plannin g |  |  | Require ment Gatheri ng |  |  | Project Initiatio n
Start Date | [8 empty] | 26-Sep |  |  |  |  | 23-Sep |  |  |  |  | 19-Sep |  |  |  | 14-Sep | [6 empty] | 07-Sep |  |  |  |  | 28-Aug | [5 empty] | 08-Aug | [5 empty] | 04-Aug | [5 empty] | 25-Jul |  | 22-Jul |  |  | 17-Jul |  |  | 15-Jul
Duration (Days) | [8 empty] | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  | 5 | [6 empty] | 7 |  |  |  |  | 10 | [5 empty] | 20 | [5 empty] | 4 | [5 empty] | 10 |  | 3 |  |  | 5 |  |  | 2
Project Calendar
 Workdays: Monday to Friday
 Work Hours: 9:00 AM to 5:00 PM
 Holidays: None specified
Resource Allocation: Website Design Project
Project Tasks and Resource Assignment
Task ID |  |  |  | Task Name | [23 empty] | Assigned Resources | [27 empty] | Resource Type
1 |  |  |  | Project Initiation | [23 empty] | Project Manager | [27 empty] | Human
2 |  |  |  | Requirement Gathering | [23 empty] | Business Analyst | [27 empty] | Human
3 |  |  |  | Site Structure Planning | [23 empty] | UX Designer | [27 empty] | Human
4 |  |  |  | Design Phase | [23 empty] | UI Designer, Graphic Designer | [27 empty] | Human
5 |  |  |  | Design Review and Approval | [23 empty] | Project Manager, Client | [27 empty] | Human
6 |  |  |  | Development Phase | [23 empty] | Web Developer, Backend Developer | [27 empty] | Human
7 |  |  |  | Content Creation | [23 empty] | Content Writer | [27 empty] | Human
8 |  |  |  | Integration and Testing | [23 empty] | QA Tester | [27 empty] | Human
9 |  |  |  | User Acceptance Testing (UAT) | [23 empty] | Client, QA Tester | [27 empty] | Human
10 |  |  |  | Final Revisions | [23 empty] | Web Developer, UI Designer | [27 empty] | Human
11 |  |  |  | Deployment | [23 empty] | Web Developer | [27 empty] | Human
12 |  |  |  | Project Closure | [23 empty] | Project Manager | [27 empty] | Human
Resource Allocation Details
Resource Name | [11 empty] | Resource Type | [11 empty] | Tasks Assigned | [14 empty] | Total Hours Estimated
Project Manager | [11 empty] | Human | [11 empty] | 1, 5, 12 | [14 empty] | 20 hours
Business Analyst | [11 empty] | Human | [11 empty] | 2 | [14 empty] | 25 hours
UX Designer | [11 empty] | Human | [11 empty] | 3 | [14 empty] | 30 hours
UI Designer | [11 empty] | Human | [11 empty] | 4, 10 | [14 empty] | 40 hours
Graphic Designer | [11 empty] | Human | [11 empty] | 4 | [14 empty] | 20 hours
Web Developer | [11 empty] | Human | [11 empty] | 6, 10, 11 | [14 empty] | 60 hours
Backend Developer | [11 empty] | Human | [11 empty] | 6 | [14 empty] | 50 hours
Content Writer | [11 empty] | Human | [11 empty] | 7 | [14 empty] | 25 hours
QA Tester | [11 empty] | Human | [11 empty] | 8, 9 | [14 empty] | 35 hours
Client | [11 empty] | Human | [11 empty] | 5, 9 | [14 empty] | 10 hours
Resource Calendar
 Workdays: Monday to Friday
 Daily Working Hours: 8 hours (adjust as per actual work schedule)
 Holidays: Adjust according to the specific region's holidays
Baseline Resource Allocation
 Baseline Assignment: Record the initial resource allocation and hours estimated for
each task.
 Tracking: Monitor actual resource usage against the baseline to ensure the project stays on track.
Notes
1. Resource Utilization: Ensure each resource's workload is balanced and adjusted
based on project progress.
2. Resource Conflicts: Resolve any conflicts where resources might be over-allocated or have overlapping tasks.
3. Communication: Regularly update resources on task status and changes to the project plan.
Baseline
 Baseline Date: 2024-07-15
 Estimated Completion Date: 2024-09-27
 Total Duration: 75 days
This table covers the basic structure of the project plan, including tasks, durations,
milestones, dependencies, calendar, resources, and baseline information.
Assignment No.:-02 (Div-A)
Execute and Monitor Project Plan for Mobile App Development
▪ Update % Complete with current task status.
▪ Review the status of each task.
▪ Compare Planned vs Actual Status
▪ Review the status of Critical Path
▪ Review resources assignation status
Mobile App Development project, incorporating execution and monitoring elements:
Project Name: Mobile App Development | [29 empty] | Start Date: 2024-07- 15 | [20 empty] | Finish Date: 2024-10- 15
Project Tasks Execution and Monitoring
Tas k ID | Task Name | [7 empty] | Durati on (Days) | [6 empty] | Star t Dat e |  |  |  | Plann ed Finish Date |  |  |  |  | Actua l Finish Date | [7 empty] | Dependen cies | [9 empty] | % Compl ete | [6 empty] | Planne d vs Actual Status |  |  |  | Resourc es |  |  |  |  | Resour ce Type
1 | Project Initiation | [7 empty] | 2 | [6 empty] | 202 4- 07- 15 |  |  |  | 2024- 07-16 |  |  |  |  | 2024- 07-16 | [7 empty] | - | [9 empty] | 100% | [6 empty] | On Schedu le |  |  |  | Project Manage r |  |  |  |  | Human
2 | Requirem ent Gathering | [7 empty] | 5 | [6 empty] | 202 4- 07- 17 |  |  |  | 2024- 07-21 |  |  |  |  | 2024- 07-22 | [7 empty] | 1 | [9 empty] | 100% | [6 empty] | 1 Day Delay |  |  |  | Busines s Analyst |  |  |  |  | Human
3 | App Structure Planning | [7 empty] | 3 | [6 empty] | 202 4- 07- 23 |  |  |  | 2024- 07-25 |  |  |  |  | 2024- 07-26 | [7 empty] | 2 | [9 empty] | 100% | [6 empty] | 1 Day Delay |  |  |  | UX Designe r |  |  |  |  | Human
4 | Design Phase | [7 empty] | 10 | [6 empty] | 202 |  |  |  | 2024- 08-05 |  |  |  |  | 2024- 08-06 | [7 empty] | 3 | [9 empty] | 100% | [6 empty] | 1 Day Delay |  |  |  | UI |  |  |  |  | Human
Designe
[16 empty] | 4- 07- | [37 empty] | r, Graphic
[16 empty] | 27 | [37 empty] | Designe
r
5 | Design Review and Approval | [7 empty] | 4 | [6 empty] | 202 4- 08- 07 |  |  |  | 2024- 08-10 |  |  |  |  | 2024- 08-11 | [7 empty] | 4 | [9 empty] | 100% | [6 empty] | 1 Day Delay |  |  |  | Project Manage r, Client |  |  |  |  | Human
6 | Developm | [7 empty] | 20 | [6 empty] | 202 |  |  |  | 2024- |  |  |  |  | In | [7 empty] | 5 | [9 empty] | 75% | [6 empty] | On |  |  |  | Mobile |  |  |  |  | Human
Tas k ID | Task Name | [7 empty] | Durati on (Days) | [6 empty] | Star t Dat e |  |  |  | Plann ed Finish Date |  |  |  |  | Actua l Finish Date | [7 empty] | Dependen cies | [9 empty] | % Compl ete | [6 empty] | Planne d vs Actual Status |  |  |  | Resourc es |  |  |  |  | Resour ce Type
| ent Phase | [14 empty] | 4- 08- 12 |  |  |  | 08-31 |  |  |  |  | Progre ss | [24 empty] | Schedu le |  |  |  | App Develop er
7 | Content Creation | [7 empty] | 10 | [6 empty] | 202 4- 08- 20 |  |  |  | 2024- 08-30 |  |  |  |  | In Progre ss | [7 empty] | 2 | [9 empty] | 50% | [6 empty] | On Schedu le |  |  |  | Content Writer |  |  |  |  | Human
8 | Integratio n and Testing | [7 empty] | 7 | [6 empty] | 202 4- 09- 01 |  |  |  | 2024- 09-07 |  |  |  |  | - | [7 empty] | 6, 7 | [9 empty] | 0% | [6 empty] | Not Started |  |  |  | QA Tester |  |  |  |  | Human
9 | User Acceptanc e Testing (UAT) | [7 empty] | 5 | [6 empty] | 202 4- 09- 08 |  |  |  | 2024- 09-12 |  |  |  |  | - | [7 empty] | 8 | [9 empty] | 0% | [6 empty] | Not Started |  |  |  | Client, QA Tester |  |  |  |  | Human
10 | Final Revisions | [7 empty] | 4 | [6 empty] | 202 |  |  |  | 2024- 09-16 |  |  |  |  | - | [7 empty] | 9 | [9 empty] | 0% | [6 empty] | Not Started |  |  |  | Mobile |  |  |  |  | Human
App
[16 empty] | 4- 09- | [37 empty] | Develop er, UI
[16 empty] | 13 | [37 empty] | Designe
r
11 | Deployme nt | [7 empty] | 3 | [6 empty] | 202 |  |  |  | 2024- 09-19 |  |  |  |  | - | [7 empty] | 10 | [9 empty] | 0% | [6 empty] | Not Started |  |  |  | Mobile |  |  |  |  | Human
[16 empty] | 4- 09- | [37 empty] | App Develop
[16 empty] | 17 | [37 empty] | er
12 | Project Closure | [7 empty] | 2 | [6 empty] | 202 4- 09- 20 |  |  |  | 2024- 09-21 |  |  |  |  | - | [7 empty] | 11 | [9 empty] | 0% | [6 empty] | Not Started |  |  |  | Project Manage r |  |  |  |  | Human
Critical Path Review
 Critical Path Tasks: 1 → 2 → 3 → 4 → 5 → 6 → 8 → 9 → 10 → 11 → 12
 Current Status:
o Tasks 1 through 5 are completed, each with a 1-day delay.
o Task 6 is 75% complete and on schedule.
o Task 8 is dependent on the completion of Task 6 and has not started yet.
Resource Assignation Status
Resource Name | [14 empty] | Assigned Tasks | [12 empty] | Current Task | [23 empty] | Status
Project Manager | [14 empty] | 1, 5, 12 | [12 empty] | Monitoring & Coordination | [23 empty] | Active
Resource Name | [14 empty] | Assigned Tasks | [12 empty] | Current Task | [23 empty] | Status
Business Analyst | [14 empty] | 2 | [12 empty] | Requirement Gathering | [23 empty] | Completed
UX Designer | [14 empty] | 3 | [12 empty] | App Structure Planning | [23 empty] | Completed
UI Designer | [14 empty] | 4, 10 | [12 empty] | Final Revisions | [23 empty] | Pending
Graphic Designer | [14 empty] | 4 | [12 empty] | Design Phase | [23 empty] | Completed
Mobile App Developer | [14 empty] | 6, 10, 11 | [12 empty] | Development Phase | [23 empty] | Active
Content Writer | [14 empty] | 7 | [12 empty] | Content Creation | [23 empty] | Active
QA Tester | [14 empty] | 8, 9 | [12 empty] | Integration and Testing | [23 empty] | Pending
Client | [14 empty] | 5, 9 | [12 empty] | Design Review & UAT | [23 empty] | Pending
Summary
 Overall Status: The project is slightly behind schedule due to a series of 1-day delays
in the initial tasks.
 Critical Path Impact: The delays in early tasks have impacted the critical path, but ongoing tasks (6 and 7) are on schedule, which might help recover some lost time.
 Resource Allocation: All resources are actively engaged or prepared for their upcoming tasks. The focus is on completing the Development Phase and Content Creation to proceed with Integration and Testing.
This table captures the on-going status and monitoring aspects of the Mobile App
Development project, including % complete, task status, and comparisons of planned vs actual progress.
Assignment No.:-02 (Div-B)
Execute and Monitor Project Plan for Website Design project
▪ Update % Complete with current task status.
▪ Review the status of each task.
▪ Compare Planned vs Actual Status
▪ Review the status of Critical Path
▪ Review resources assignation status
The execution and monitoring plan for the Website Design project:
Project Name: Website Design Project | [27 empty] | Start Date: 2024-07-15 | [20 empty] | Finish Date: 2024-10-15
Project Tasks Execution and Monitoring
Tas k ID | Task Name | [7 empty] | Durati on (Days) | [6 empty] | Star t Dat e |  |  |  | Plann ed Finish Date |  |  |  |  | Actua l Finish Date | [7 empty] | Dependen cies | [9 empty] | % Compl ete | [6 empty] | Planne d vs Actual Status |  |  |  | Resourc es |  |  |  |  | Resour ce Type
1 | Project Initiation | [7 empty] | 2 | [6 empty] | 202 4- 07- 15 |  |  |  | 2024- 07-16 |  |  |  |  | 2024- 07-16 | [7 empty] | - | [9 empty] | 100% | [6 empty] | On Schedu le |  |  |  | Project Manage r |  |  |  |  | Human
2 | Requirem ent Gathering | [7 empty] | 5 | [6 empty] | 202 4- 07- 17 |  |  |  | 2024- 07-21 |  |  |  |  | 2024- 07-22 | [7 empty] | 1 | [9 empty] | 100% | [6 empty] | 1 Day Delay |  |  |  | Busines s Analyst |  |  |  |  | Human
3 | Site Structure Planning | [7 empty] | 3 | [6 empty] | 202 4- 07- 22 |  |  |  | 2024- 07-24 |  |  |  |  | 2024- 07-25 | [7 empty] | 2 | [9 empty] | 100% | [6 empty] | 1 Day Delay |  |  |  | UX Designe r |  |  |  |  | Human
4 | Design Phase | [7 empty] | 10 | [6 empty] | 202 |  |  |  | 2024- 08-03 |  |  |  |  | 2024- 08-05 | [7 empty] | 3 | [9 empty] | 100% | [6 empty] | 2 Days Delay |  |  |  | UI |  |  |  |  | Human
Designe
[16 empty] | 4- 07- | [37 empty] | r, Graphic
[16 empty] | 25 | [37 empty] | Designe
r
5 | Design Review and Approval | [7 empty] | 4 | [6 empty] | 202 4- 08- 04 |  |  |  | 2024- 08-07 |  |  |  |  | 2024- 08-09 | [7 empty] | 4 | [9 empty] | 100% | [6 empty] | 2 Days Delay |  |  |  | Project Manage r, Client |  |  |  |  | Human
6 | Developm ent Phase | [7 empty] | 20 | [6 empty] | 202 4- 08- 08 |  |  |  | 2024- 08-27 |  |  |  |  | In Progre ss | [7 empty] | 5 | [9 empty] | 70% | [6 empty] | On Schedu le |  |  |  | Web |  |  |  |  | Human
Develop er, Backend Develop
er
Tas k ID | Task Name | [7 empty] | Durati on (Days) | [6 empty] | Star t Dat e |  |  |  | Plann ed Finish Date |  |  |  |  | Actua l Finish Date | [7 empty] | Dependen cies | [9 empty] | % Compl ete | [6 empty] | Planne d vs Actual Status |  |  |  | Resourc es |  |  |  |  | Resour ce Type
7 | Content Creation | [7 empty] | 10 | [6 empty] | 202 4- 08- 28 |  |  |  | 2024- 09-06 |  |  |  |  | In Progre ss | [7 empty] | 2 | [9 empty] | 50% | [6 empty] | On Schedu le |  |  |  | Content Writer |  |  |  |  | Human
8 | Integratio n and Testing | [7 empty] | 7 | [6 empty] | 202 4- 09- 07 |  |  |  | 2024- 09-13 |  |  |  |  | - | [7 empty] | 6, 7 | [9 empty] | 0% | [6 empty] | Not Started |  |  |  | QA Tester |  |  |  |  | Human
9 | User Acceptanc e Testing (UAT) | [7 empty] | 5 | [6 empty] | 202 4- 09- 14 |  |  |  | 2024- 09-18 |  |  |  |  | - | [7 empty] | 8 | [9 empty] | 0% | [6 empty] | Not Started |  |  |  | Client, QA Tester |  |  |  |  | Human
10 | Final Revisions | [7 empty] | 4 | [6 empty] | 202 4- 09- 19 |  |  |  | 2024- 09-22 |  |  |  |  | - | [7 empty] | 9 | [9 empty] | 0% | [6 empty] | Not Started |  |  |  | Web Develop er, UI Designe r |  |  |  |  | Human
11 | Deployme nt | [7 empty] | 3 | [6 empty] | 202 4- 09- 23 |  |  |  | 2024- 09-25 |  |  |  |  | - | [7 empty] | 10 | [9 empty] | 0% | [6 empty] | Not Started |  |  |  | Web Develop er |  |  |  |  | Human
12 | Project Closure | [7 empty] | 2 | [6 empty] | 202 4- 09- 26 |  |  |  | 2024- 09-27 |  |  |  |  | - | [7 empty] | 11 | [9 empty] | 0% | [6 empty] | Not Started |  |  |  | Project Manage r |  |  |  |  | Human
Critical Path Review
 Critical Path Tasks: 1 → 2 → 3 → 4 → 5 → 6 → 8 → 9 → 10 → 11 → 12
 Current Status:
o Tasks 1 through 5 are completed, each with delays ranging from 1 to 2 days.
o Task 6 is 70% complete and on schedule.
o Task 8 is dependent on the completion of Task 6 and has not started yet.
Resource Assignation Status
Resource Name | [11 empty] | Assigned Tasks | [11 empty] | Current Task | [24 empty] | Status
Project Manager | [11 empty] | 1, 5, 12 | [11 empty] | Monitoring & Coordination | [24 empty] | Active
Business Analyst | [11 empty] | 2 | [11 empty] | Requirement Gathering | [24 empty] | Completed
UX Designer | [11 empty] | 3 | [11 empty] | Site Structure Planning | [24 empty] | Completed
UI Designer | [11 empty] | 4, 10 | [11 empty] | Final Revisions | [24 empty] | Pending
Graphic Designer | [11 empty] | 4 | [11 empty] | Design Phase | [24 empty] | Completed
Resource Name | [11 empty] | Assigned Tasks | [11 empty] | Current Task | [24 empty] | Status
Web Developer | [11 empty] | 6, 10, 11 | [11 empty] | Development Phase | [24 empty] | Active
Backend Developer | [11 empty] | 6 | [11 empty] | Development Phase | [24 empty] | Active
Content Writer | [11 empty] | 7 | [11 empty] | Content Creation | [24 empty] | Active
QA Tester | [11 empty] | 8, 9 | [11 empty] | Integration and Testing | [24 empty] | Pending
Client | [11 empty] | 5, 9 | [11 empty] | Design Review & UAT | [24 empty] | Pending
Summary
 Overall Status: The project has experienced minor delays in the initial tasks but is
generally progressing well.
 Critical Path Impact: The delays in early tasks have impacted the critical path, but ongoing tasks (6 and 7) are on schedule, which might help recover some lost time.
 Resource Allocation: All resources are actively engaged or prepared for their upcoming tasks. The focus is on completing the Development Phase and Content Creation to proceed with Integration and Testing.
This table captures the ongoing status and monitoring aspects of the Website Design project,
including % complete, task status, and comparisons of planned vs actual progress.
Assignment No.:-03 (Div-A)
Generate Dashboard and Reports for Mobile App Development
 Dashboard
o Project Overview o Cost Overview
o Upcoming Tasks
 Resource Reports
o Over-allocated Resources o Resource Overview
 Cost Reports
o Earned Value Report
o Resource Cost Overview o Task Cost Overview
 Progress Reports
o Critical Tasks
o Milestone Report o Slipping Tasks
Mobile App Development Dashboard and Reports
Dashboard
Project Overview
Metric | [10 empty] | Value
Project Name | [10 empty] | Mobile App Development
Start Date | [10 empty] | 2024-07-15
Planned Finish Date | [10 empty] | 2024-10-15
Actual Finish Date | [10 empty] | In Progress
Current Status | [10 empty] | On Schedule
% Complete | [10 empty] | 65%
Cost Overview
Category | [6 empty] | Planned Cost | [10 empty] | Actual Cost | [8 empty] | Variance
Total Cost | [6 empty] | 100000 | [10 empty] | 65000 | [8 empty] | 35000
Resource Cost | [6 empty] | 80000 | [10 empty] | 52000 | [8 empty] | 28000
Other Costs | [6 empty] | 20000 | [10 empty] | 13000 | [8 empty] | 7000
Upcoming Tasks
Task ID |  |  | Task Name | [21 empty] | Start Date | [9 empty] | Due Date | [9 empty] | Assigned To
8 |  |  | Integration and Testing | [21 empty] | 2024-09- 01 | [9 empty] | 2024-09- 07 | [9 empty] | QA Tester
9 |  |  | User Acceptance Testing (UAT) | [21 empty] | 2024-09- 08 | [9 empty] | 2024-09- 12 | [9 empty] | Client, QA Tester
10 |  |  | Final Revisions | [21 empty] | 2024-09- 13 | [9 empty] | 2024-09- 16 | [9 empty] | Mobile App Developer, UI Designer
11 |  |  | Deployment | [21 empty] | 2024-09- 17 | [9 empty] | 2024-09- 19 | [9 empty] | Mobile App Developer
Resource Reports
Over-allocated Resources
Resource Name | [12 empty] | Assigned Tasks | [10 empty] | Over-allocated Tasks
Mobile App Developer | [12 empty] | 6, 10, 11 | [10 empty] | None
Resource Overview
Resource Name | [12 empty] | Role | [15 empty] | Current Task | [21 empty] | Status
Project Manager | [12 empty] | Oversees project | [15 empty] | Monitoring & Coordination | [21 empty] | Active
Business Analyst | [12 empty] | Gathers requirements | [15 empty] | Requirement Gathering | [21 empty] | Completed
UX Designer | [12 empty] | Plans site structure | [15 empty] | App Structure Planning | [21 empty] | Completed
UI Designer | [12 empty] | Creates UI designs | [15 empty] | Final Revisions | [21 empty] | Pending
Graphic Designer | [12 empty] | Creates graphics | [15 empty] | Design Phase | [21 empty] | Completed
Mobile App Developer | [12 empty] | Develops frontend | [15 empty] | Development Phase | [21 empty] | Active
Content Writer | [12 empty] | Writes content | [15 empty] | Content Creation | [21 empty] | Active
QA Tester | [12 empty] | Conducts testing | [15 empty] | Integration and Testing | [21 empty] | Pending
Client | [12 empty] | Provides approval | [15 empty] | Design Review & UAT | [21 empty] | Pending
Cost Reports
Earned Value Report
Metric | [13 empty] | Value
Planned Value (PV) | [13 empty] | 70000
Earned Value (EV) | [13 empty] | 65000
Actual Cost (AC) | [13 empty] | 65000
Schedule Variance (SV) | [13 empty] | -5000
Cost Variance (CV) | [13 empty] | 0
Resource Cost Overview
Resource Name | [12 empty] | Planned Cost | [8 empty] | Actual Cost | [11 empty] | Variance
Project Manager | [12 empty] | 10000 | [8 empty] | 8000 | [11 empty] | 2000
Business Analyst | [12 empty] | 8000 | [8 empty] | 7000 | [11 empty] | 1000
UX Designer | [12 empty] | 12000 | [8 empty] | 12000 | [11 empty] | 0
Resource Name | [12 empty] | Planned Cost | [8 empty] | Actual Cost | [11 empty] | Variance
UI Designer | [12 empty] | 15000 | [8 empty] | 12000 | [11 empty] | 3000
Graphic Designer | [12 empty] | 10000 | [8 empty] | 10000 | [11 empty] | 0
Mobile App Developer | [12 empty] | 20000 | [8 empty] | 15000 | [11 empty] | 5000
Content Writer | [12 empty] | 5000 | [8 empty] | 3000 | [11 empty] | 2000
QA Tester | [12 empty] | 10000 | [8 empty] | 5000 | [11 empty] | 5000
Client | [12 empty] | 0 | [8 empty] | 0 | [11 empty] | 0
Task Cost Overview
Task ID |  |  | Task Name | [22 empty] | Planned Cost | [11 empty] | Actual Cost | [9 empty] | Variance
1 |  |  | Project Initiation | [22 empty] | 2000 | [11 empty] | 1500 | [9 empty] | 500
2 |  |  | Requirement Gathering | [22 empty] | 5000 | [11 empty] | 4000 | [9 empty] | 1000
3 |  |  | App Structure Planning | [22 empty] | 4000 | [11 empty] | 3500 | [9 empty] | 500
4 |  |  | Design Phase | [22 empty] | 10000 | [11 empty] | 8500 | [9 empty] | 1500
5 |  |  | Design Review and Approval | [22 empty] | 3000 | [11 empty] | 2500 | [9 empty] | 500
6 |  |  | Development Phase | [22 empty] | 30000 | [11 empty] | 20000 | [9 empty] | 10000
7 |  |  | Content Creation | [22 empty] | 5000 | [11 empty] | 3000 | [9 empty] | 2000
8 |  |  | Integration and Testing | [22 empty] | 8000 | [11 empty] | 4000 | [9 empty] | 4000
9 |  |  | User Acceptance Testing (UAT) | [22 empty] | 5000 | [11 empty] | 0 | [9 empty] | 5000
10 |  |  | Final Revisions | [22 empty] | 5000 | [11 empty] | 0 | [9 empty] | 5000
11 |  |  | Deployment | [22 empty] | 3000 | [11 empty] | 0 | [9 empty] | 3000
12 |  |  | Project Closure | [22 empty] | 2000 | [11 empty] | 0 | [9 empty] | 2000
Progress Reports
Critical Tasks
Task ID |  |  | Task Name | [22 empty] | Planned Finish Date | [17 empty] | Actual Finish Date | [12 empty] | Status
1 |  |  | Project Initiation | [22 empty] | 2024-07-16 | [17 empty] | 2024-07-16 | [12 empty] | Completed
2 |  |  | Requirement Gathering | [22 empty] | 2024-07-21 | [17 empty] | 2024-07-22 | [12 empty] | Completed
3 |  |  | App Structure Planning | [22 empty] | 2024-07-25 | [17 empty] | 2024-07-26 | [12 empty] | Completed
4 |  |  | Design Phase | [22 empty] | 2024-08-05 | [17 empty] | 2024-08-06 | [12 empty] | Completed
5 |  |  | Design Review and Approval | [22 empty] | 2024-08-10 | [17 empty] | 2024-08-11 | [12 empty] | Completed
6 |  |  | Development Phase | [22 empty] | 2024-08-31 | [17 empty] | In Progress | [12 empty] | On Schedule
8 |  |  | Integration and Testing | [22 empty] | 2024-09-07 | [17 empty] | - | [12 empty] | Not Started
9 |  |  | User Acceptance Testing (UAT) | [22 empty] | 2024-09-12 | [17 empty] | - | [12 empty] | Not Started
10 |  |  | Final Revisions | [22 empty] | 2024-09-16 | [17 empty] | - | [12 empty] | Not Started
11 |  |  | Deployment | [22 empty] | 2024-09-19 | [17 empty] | - | [12 empty] | Not Started
12 |  |  | Project Closure | [22 empty] | 2024-09-21 | [17 empty] | - | [12 empty] | Not Started
Milestone Report
Milestone | [20 empty] | Planned Date | [10 empty] | Actual Date | [9 empty] | Status
Project Kickoff | [20 empty] | 2024-07-15 | [10 empty] | 2024-07-15 | [9 empty] | Completed
Requirement Document | [20 empty] | 2024-07-21 | [10 empty] | 2024-07-22 | [9 empty] | Completed
Milestone | [20 empty] | Planned Date | [10 empty] | Actual Date | [9 empty] | Status
Site Map Created | [20 empty] | 2024-07-25 | [10 empty] | 2024-07-26 | [9 empty] | Completed
Initial Design Completed | [20 empty] | 2024-08-03 | [10 empty] | 2024-08-06 | [9 empty] | Completed
Design Approved | [20 empty] | 2024-08-07 | [10 empty] | 2024-08-11 | [9 empty] | Completed
Frontend and Backend Completed | [20 empty] | 2024-08-31 | [10 empty] | - | [9 empty] | In Progress
Content Ready | [20 empty] | 2024-09-06 | [10 empty] | - | [9 empty] | In Progress
Testing Completed | [20 empty] | 2024-09-13 | [10 empty] | - | [9 empty] | Not Started
UAT Completed | [20 empty] | 2024-09-18 | [10 empty] | - | [9 empty] | Not Started
Revisions Completed | [20 empty] | 2024-09-22 | [10 empty] | - | [9 empty] | Not Started
Site Live | [20 empty] | 2024-09-25 | [10 empty] | - | [9 empty] | Not Started
Project Completed | [20 empty] | 2024-09-27 | [10 empty] | - | [9 empty] | Not Started
Slipping Tasks
Task ID |  |  | Task Name | [19 empty] | Planned Finish Date | [17 empty] | Actual Finish Date | [13 empty] | Status |  |  |  |  | Delay
2 |  |  | Requirement Gathering | [19 empty] | 2024-07-21 | [17 empty] | 2024-07-22 | [13 empty] | Completed |  |  |  |  | 1 Day
3 |  |  | App Structure Planning | [19 empty] | 2024-07-25 | [17 empty] | 2024-07-26 | [13 empty] | Completed |  |  |  |  | 1 Day
4 |  |  | Design Phase | [19 empty] | 2024-08-05 | [17 empty] | 2024-08-06 | [13 empty] | Completed |  |  |  |  | 1 Day
5 |  |  | Design Review and Approval | [19 empty] | 2024-08-10 | [17 empty] | 2024-08-11 | [13 empty] | Completed |  |  |  |  | 1 Day
This table captures the detailed status and monitoring elements of the Mobile App
Development project, including dashboards for project overview, cost overview, and upcoming tasks, as well as various resource, cost, and progress reports.
Assignment No.:-03 (Div-B)
Generate Dashboard and Reports for Website Design
 Dashboard
o Project Overview o Cost Overview
o Upcoming Tasks
 Resource Reports
o Over-allocated Resources o Resource Overview
 Cost Reports
o Earned Value Report
o Resource Cost Overview o Task Cost Overview
 Progress Reports
o Critical Tasks
o Milestone Report o Slipping Tasks
Website Design Dashboard and Reports
Dashboard
Project Overview
Metric | [10 empty] | Value
Project Name | [10 empty] | Website Design
Start Date | [10 empty] | 2024-07-15
Planned Finish Date | [10 empty] | 2024-10-15
Actual Finish Date | [10 empty] | In Progress
Current Status | [10 empty] | On Schedule
% Complete | [10 empty] | 65%
Cost Overview
Category | [6 empty] | Planned Cost | [10 empty] | Actual Cost | [8 empty] | Variance
Total Cost | [6 empty] | 80000 | [10 empty] | 52000 | [8 empty] | 28000
Resource Cost | [6 empty] | 60000 | [10 empty] | 39000 | [8 empty] | 21000
Other Costs | [6 empty] | 20000 | [10 empty] | 13000 | [8 empty] | 7000
Upcoming Tasks
Task ID |  |  | Task Name | [22 empty] | Start Date | [9 empty] | Due Date | [9 empty] | Assigned To
8 |  |  | Integration and Testing | [22 empty] | 2024-09-07 | [9 empty] | 2024-09-13 | [9 empty] | QA Tester
9 |  |  | User Acceptance Testing (UAT) | [22 empty] | 2024-09-14 | [9 empty] | 2024-09-18 | [9 empty] | Client, QA Tester
10 |  |  | Final Revisions | [22 empty] | 2024-09-19 | [9 empty] | 2024-09-22 | [9 empty] | Web Developer, UI Designer
11 |  |  | Deployment | [22 empty] | 2024-09-23 | [9 empty] | 2024-09-25 | [9 empty] | Web Developer
Resource Reports
Over-allocated Resources
Resource Name | [7 empty] | Assigned Tasks | [12 empty] | Over-allocated Tasks
Web Developer | [7 empty] | 6, 10, 11 | [12 empty] | None
Resource Overview
Resource Name | [9 empty] | Role | [15 empty] | Current Task | [21 empty] | Status
Project Manager | [9 empty] | Oversees project | [15 empty] | Monitoring & Coordination | [21 empty] | Active
Business Analyst | [9 empty] | Gathers requirements | [15 empty] | Requirement Gathering | [21 empty] | Completed
UX Designer | [9 empty] | Plans site structure | [15 empty] | Site Structure Planning | [21 empty] | Completed
UI Designer | [9 empty] | Creates UI designs | [15 empty] | Final Revisions | [21 empty] | Pending
Graphic Designer | [9 empty] | Creates graphics | [15 empty] | Design Phase | [21 empty] | Completed
Web Developer | [9 empty] | Develops frontend | [15 empty] | Development Phase | [21 empty] | Active
Backend Developer | [9 empty] | Develops backend | [15 empty] | Development Phase | [21 empty] | Active
Content Writer | [9 empty] | Writes content | [15 empty] | Content Creation | [21 empty] | Active
QA Tester | [9 empty] | Conducts testing | [15 empty] | Integration and Testing | [21 empty] | Pending
Client | [9 empty] | Provides approval | [15 empty] | Design Review & UAT | [21 empty] | Pending
Cost Reports
Earned Value Report
Metric | [13 empty] | Value
Planned Value (PV) | [13 empty] | 55000
Earned Value (EV) | [13 empty] | 52000
Actual Cost (AC) | [13 empty] | 52000
Schedule Variance (SV) | [13 empty] | -3000
Cost Variance (CV) | [13 empty] | 0
Resource Cost Overview
Resource Name | [9 empty] | Planned Cost | [10 empty] | Actual Cost | [9 empty] | Variance
Project Manager | [9 empty] | 10000 | [10 empty] | 8000 | [9 empty] | 2000
Business Analyst | [9 empty] | 8000 | [10 empty] | 7000 | [9 empty] | 1000
UX Designer | [9 empty] | 10000 | [10 empty] | 10000 | [9 empty] | 0
UI Designer | [9 empty] | 15000 | [10 empty] | 12000 | [9 empty] | 3000
Resource Name | [9 empty] | Planned Cost | [10 empty] | Actual Cost | [9 empty] | Variance
Graphic Designer | [9 empty] | 10000 | [10 empty] | 10000 | [9 empty] | 0
Web Developer | [9 empty] | 20000 | [10 empty] | 14000 | [9 empty] | 6000
Backend Developer | [9 empty] | 12000 | [10 empty] | 10000 | [9 empty] | 2000
Content Writer | [9 empty] | 5000 | [10 empty] | 3000 | [9 empty] | 2000
QA Tester | [9 empty] | 10000 | [10 empty] | 5000 | [9 empty] | 5000
Client | [9 empty] | 0 | [10 empty] | 0 | [9 empty] | 0
Task Cost Overview
Task ID |  |  | Task Name | [22 empty] | Planned Cost | [11 empty] | Actual Cost | [9 empty] | Variance
1 |  |  | Project Initiation | [22 empty] | 2000 | [11 empty] | 1500 | [9 empty] | 500
2 |  |  | Requirement Gathering | [22 empty] | 5000 | [11 empty] | 4000 | [9 empty] | 1000
3 |  |  | Site Structure Planning | [22 empty] | 4000 | [11 empty] | 3500 | [9 empty] | 500
4 |  |  | Design Phase | [22 empty] | 10000 | [11 empty] | 8500 | [9 empty] | 1500
5 |  |  | Design Review and Approval | [22 empty] | 3000 | [11 empty] | 2500 | [9 empty] | 500
6 |  |  | Development Phase | [22 empty] | 30000 | [11 empty] | 18000 | [9 empty] | 12000
7 |  |  | Content Creation | [22 empty] | 5000 | [11 empty] | 3000 | [9 empty] | 2000
8 |  |  | Integration and Testing | [22 empty] | 8000 | [11 empty] | 4000 | [9 empty] | 4000
9 |  |  | User Acceptance Testing (UAT) | [22 empty] | 5000 | [11 empty] | 0 | [9 empty] | 5000
10 |  |  | Final Revisions | [22 empty] | 5000 | [11 empty] | 0 | [9 empty] | 5000
11 |  |  | Deployment | [22 empty] | 3000 | [11 empty] | 0 | [9 empty] | 3000
12 |  |  | Project Closure | [22 empty] | 2000 | [11 empty] | 0 | [9 empty] | 2000
Progress Reports
Critical Tasks
Task ID |  |  | Task Name | [22 empty] | Planned Finish Date | [17 empty] | Actual Finish Date | [12 empty] | Status
1 |  |  | Project Initiation | [22 empty] | 2024-07-16 | [17 empty] | 2024-07-16 | [12 empty] | Completed
2 |  |  | Requirement Gathering | [22 empty] | 2024-07-21 | [17 empty] | 2024-07-22 | [12 empty] | Completed
3 |  |  | Site Structure Planning | [22 empty] | 2024-07-24 | [17 empty] | 2024-07-25 | [12 empty] | Completed
4 |  |  | Design Phase | [22 empty] | 2024-08-03 | [17 empty] | 2024-08-05 | [12 empty] | Completed
5 |  |  | Design Review and Approval | [22 empty] | 2024-08-07 | [17 empty] | 2024-08-09 | [12 empty] | Completed
6 |  |  | Development Phase | [22 empty] | 2024-08-27 | [17 empty] | In Progress | [12 empty] | On Schedule
8 |  |  | Integration and Testing | [22 empty] | 2024-09-13 | [17 empty] | - | [12 empty] | Not Started
9 |  |  | User Acceptance Testing (UAT) | [22 empty] | 2024-09-18 | [17 empty] | - | [12 empty] | Not Started
10 |  |  | Final Revisions | [22 empty] | 2024-09-22 | [17 empty] | - | [12 empty] | Not Started
11 |  |  | Deployment | [22 empty] | 2024-09-25 | [17 empty] | - | [12 empty] | Not Started
12 |  |  | Project Closure | [22 empty] | 2024-09-27 | [17 empty] | - | [12 empty] | Not Started
Milestone Report
Milestone | [20 empty] | Planned Date | [10 empty] | Actual Date | [9 empty] | Status
Project Kickoff | [20 empty] | 2024-07-15 | [10 empty] | 2024-07-15 | [9 empty] | Completed
Requirement Document | [20 empty] | 2024-07-21 | [10 empty] | 2024-07-22 | [9 empty] | Completed
Milestone | [20 empty] | Planned Date | [10 empty] | Actual Date | [9 empty] | Status
Site Map Created | [20 empty] | 2024-07-24 | [10 empty] | 2024-07-25 | [9 empty] | Completed
Initial Design Completed | [20 empty] | 2024-08-03 | [10 empty] | 2024-08-05 | [9 empty] | Completed
Design Approved | [20 empty] | 2024-08-07 | [10 empty] | 2024-08-09 | [9 empty] | Completed
Frontend and Backend Completed | [20 empty] | 2024-08-27 | [10 empty] | - | [9 empty] | In Progress
Content Ready | [20 empty] | 2024-09-06 | [10 empty] | - | [9 empty] | In Progress
Testing Completed | [20 empty] | 2024-09-13 | [10 empty] | - | [9 empty] | Not Started
UAT Completed | [20 empty] | 2024-09-18 | [10 empty] | - | [9 empty] | Not Started
Revisions Completed | [20 empty] | 2024-09-22 | [10 empty] | - | [9 empty] | Not Started
Site Live | [20 empty] | 2024-09-25 | [10 empty] | - | [9 empty] | Not Started
Project Completed | [20 empty] | 2024-09-27 | [10 empty] | - | [9 empty] | Not Started
Slipping Tasks
Task ID |  |  | Task Name | [19 empty] | Planned Finish Date | [17 empty] | Actual Finish Date | [13 empty] | Status |  |  |  |  | Delay
2 |  |  | Requirement Gathering | [19 empty] | 2024-07-21 | [17 empty] | 2024-07-22 | [13 empty] | Completed |  |  |  |  | 1 Day
3 |  |  | Site Structure Planning | [19 empty] | 2024-07-24 | [17 empty] | 2024-07-25 | [13 empty] | Completed |  |  |  |  | 1 Day
4 |  |  | Design Phase | [19 empty] | 2024-08-03 | [17 empty] | 2024-08-05 | [13 empty] | Completed |  |  |  |  | 2 Days
5 |  |  | Design Review and Approval | [19 empty] | 2024-08-07 | [17 empty] | 2024-08-09 | [13 empty] | Completed |  |  |  |  | 2 Days
This table captures the detailed status and monitoring elements of the Website Design project,
including dashboards for project overview, cost overview, and upcoming tasks, as well as various resource, cost, and progress reports.